## ProjectSchedule
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | ASP Group 8 (Tutor Group 01), after midterm | [5 empty] | SIMPLE GANTT CHART by Vertex42.com
Enter Company Name in cell B2. | Alex Hoi Chu, Dimitri Vlachos, Freda Xiaoyun Yu, Jeremy Matthews | [5 empty] | https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Pooject Start: label is in cell C3. |  | Project Start: |  | 2022-01-10
|  | Project End: |  | 2022-03-28
20 | Notes: enter format like '2021/09/15'. | Display Week: |  | 1 |  |  | 2022-01-10 | [6 empty] | 2022-01-17 | [6 empty] | 2022-01-24 | [6 empty] | 2022-01-31 | [6 empty] | 2022-02-07 | [6 empty] | 2022-02-14 | [6 empty] | 2022-02-21 | [6 empty] | 2022-02-28
Display | You can change the 'Display Week' num to see the weeks later. | time axis 2022-01-10 to 2022-03-06
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2022-01-10 to 2022-03-06
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the curren day within the project schedule.
Cell B8 contains the Phase 1 sample title. Enter a new Title in cell B8. Enter a name to assign the phase to, if it applies for your project, in cell C8. Enter Progress for the entire phase, if it applies for your project, in cell D8. Enter the start and end dates for the entire phase, if it applies for your project, in cells E8 and F8. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | Phase 1 Management, Plan, Design
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progres of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | Change of any design | All | 90% | 2022-01-10 | 2022-03-28 | 78
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Time scale chart | Freda, Dimitri | 90% | 2022-01-10 | 2022-01-28 | 19
| Meeting time arrangement | Dimitri | 100% | 2022-01-10 | 2022-01-30
| Settle dowm the main story | All | 100% | 2022-01-10 | 2022-03-28 | 78
| Version control platform settle down | All | 100% | 2022-01-10 | 2022-01-15
| Design the towers & characters | Dimitri, Jeremy, Freda | 100% | 2022-01-10 | 2022-01-25
| Design the maps | Jeremy, Alex | 90% | 2022-01-10 | 2022-01-25
| Design the background | Jeremy, Dimitri, Freda | 100% | 2022-01-10 | 2022-01-25
| Design the HUD | Jeremy, Dimitri | 100% | 2022-01-10 | 2022-01-25
| Design the buttons | Freda, Dimitri | 100% | 2022-01-10 | 2022-01-25
| bg music writing | Freda | 80% | 2022-01-10 | 2022-03-24
The cell at right contains the Phase 2 sample title. You can create a new phase at any time within column B. This project schedule does not require phases. To remove the phase, simply delete the row. To create a new phase block in this row, enter a new Title in cell at right. To continue adding tasks to the phase above, enter a new row above this one and fill in the task data as in cell A9's instruction. Update the Phase details in cell at right based on cell A8's instruction. Continue navigating down column A cells to learn more. If you haven't added any new rows in this worksheet, you will find 2 additional sample phase blocks have been created for you in cells B20 and B26. Otherwise, navigate through column A cells to find the additional blocks. Repeat the instructions from cells A8 and A9 whenever you need to. | Phase 2 Requirements Change
| Spread out questionnaires | Freda | 100% | 2022-01-10 | 2022-02-26
| Questionnaires for user testing | Freda | 100% | 2022-02-09 | 2022-03-28
| Change of Requirements from users | Alex, Dimitri | 80% | 2022-01-10 | 2022-03-28
| Change of UML | Alex, Dimitri | 90% | 2022-01-10 | 2022-03-28
| Potential Change of specification | Alex | 90% | 2022-01-10 | 2022-03-28
Sample phase title block | Phase 3 Coding
| Initial coding | Matthews, Vlachos | 90% | 2022-01-10 | 2022-01-25 | 16
| Writing of 'game start' | Alex | 90% | 2022-01-10 | 2022-03-13 | 63
| Writing of 'initial load' | Alex | 90% | 2022-01-10 | 2022-03-13 | 63
| Writing of 'main menu' | Alex | 90% | 2022-01-10 | 2022-03-13
| Writing of 'level select' | Alex | 90% | 2022-01-10 | 2022-03-13 | 63
| Writing of 'GameStats' | Alex | 90% | 2022-01-10 | 2022-03-13
| Writing of 'HUD' | Alex | 90% | 2022-01-10 | 2022-03-13
| Writing of 'Site' | Alex | 90% | 2022-01-10 | 2022-03-13
| Writing of 'TowerMenu' | Alex | 90% | 2022-01-10 | 2022-03-13
| Writing of 'Enemy' | Alex | 90% | 2022-01-10 | 2022-03-13
| Writing of 'MenuBuy' | Alex | 90% | 2022-01-10 | 2022-03-13
| Writing of 'MenuStats' | Alex | 90% | 2022-01-10 | 2022-03-13
| Writing of 'BuyTower' | Alex | 90% | 2022-01-10 | 2022-03-13
| Writing of 'LevelComplete' | Alex | 90% | 2022-01-10 | 2022-03-13
| Writing of 'GameOver' | Alex | 0% | 2022-01-10 | 2022-03-13
| Make Resource object | Alex | 100% | 2022-02-02 | 2022-02-03
| Check resource data integrity | Alex | 100% | 2022-02-21 | 2022-02-23
| Make states | Alex | 100% | 2022-01-17 | 2022-01-20
| Make map | Alex | 100% | 2022-01-23 | 2022-01-24
| Make origin | Alex | 100% | 2022-01-23 | 2022-01-24
| Make path | Alex | 100% | 2022-01-23 | 2022-01-24
| Make destination | Alex | 100% | 2022-01-23 | 2022-01-24
| Make decoration | Alex | 100% | 2022-02-08 | 2022-02-10
| Make enemy objects | Alex | 100% | 2022-01-21 | 2022-01-22
| Make wave data | Alex | 100% | 2022-02-05 | 2022-02-06
| Make tower objects | Alex | 100% | 2022-01-25 | 2022-01-27
| Make bullet objects | Alex | 100% | 2022-01-29 | 2022-01-29
| Make AOE towers | Alex | 100% | 2022-02-16 | 2022-02-17
| Make HP bars | Alex | 100% | 2022-02-18 | 2022-02-20
| Make setting items | Alex | 100% | 2022-02-01 | 2022-02-01
| Make tower menu objects | Alex | 100% | 2022-02-01 | 2022-02-01
| Convert map data to tiles | Alex | 100% | 2022-02-08 | 2022-02-10
| Add sound | Alex | 100% | 2022-02-13 | 2022-03-08
| Convert resource data to json files | Alex | 100% | 2022-02-14 | 2022-03-09
| Add assets | Alex, Freda | 100% | 2022-02-15 | 2022-03-10
| Make treasure box | Freda | 100% | 2022-03-01 | 2022-03-07
| Make happy ending page | Jeremy, Freda | 100% | 2022-03-01 | 2022-03-07
| Convert game into executable webpage | Jeremy | 90% | 2022-03-02 | 2022-03-10
| Refine the codes | Jeremy, Alex, Dimitri | 90% | 2022-03-03 | 2022-03-28
Sample phase title block | Phase 4 Testing
| Technical testing (many rounds) | Jeremy | 90% | 2022-01-30 | 2022-03-28
| Security testing |  | 0% | 2022-01-30 | 2022-03-28
| Accessibility testing | Freda | 70% | 2022-01-30 | 2022-03-28 | 58
| Usability testing | Freda | 80% | 2022-01-30 | 2022-03-28 | 58
| User testing (many rounds) | Freda | 70% | 2022-01-30 | 2022-03-28 | 58
|  |  | 0% | 2022-01-30 | 2022-03-28 | 58
|  |  | 0% | 2022-01-30 | 2022-03-28 | 58
Sample phase title block | (Phase 5 On Market)
| Determine how users use our game | Jeremy | 100% | 2022-02-24 | 2022-03-08
| Release the game with a link | Jeremy | 100% | 2022-02-24 | 2022-03-08
| Release-platform settle down | All | 0% | 2022-01-10 | 2022-03-08
| Determine target market based on users |  | 0% | 2022-01-10 | 2022-02-26
| Read platform documents |  | 0% | 2022-02-09 | 2022-03-13
| Release the game to the platform |  | 0% | 2022-01-30 | 2022-03-13
| Gather user feedbacks |  | 0% | 2022-02-09 | 2022-03-28
| Update product |  | 0% | 2022-02-09 | 2022-03-28
Sample phase title block | Phase 5 Documents for Final
| Read rubric | All | 80% | 2022-02-19 | 2022-03-28
| rough draft | Freda | 100% | 2022-02-19 | 2022-03-18
| Background | Freda | 100% | 2022-02-19 | 2022-03-28
| Planning & Research | Freda | 90% | 2022-02-19 | 2022-03-28
| Prototyping & Iteration | Freda | 100% | 2022-02-19 | 2022-03-28
| Technological Design | Freda, Alex | 50% | 2022-03-01 | 2022-03-28
| Aesthetic Design | Freda | 90% | 2022-03-01 | 2022-03-28
| System Development | Jeremy | 70% | 2022-03-01 | 2022-03-28
| Tech testing writing | Jeremy | 70% | 2022-03-02 | 2022-03-28
| Analysis | Freda | 100% | 2022-03-01 | 2022-03-28
| Evaluation | Freda | 90% | 2022-03-01 | 2022-03-28
| Individual reflections | All | 80% | 2022-02-27 | 2022-03-28
| Download Github version control log | All | 0% | 2022-02-28 | 2022-03-28
| Put Git log & other files into a zip | All | 30% | 2022-02-27 | 2022-03-28
| Refine Gantt chart | All | 80% | 2022-02-28 | 2022-03-28
| Refine final proposal: Background | All |  | 2022-03-01 | 2022-03-28
| Refine final proposal: Summary | All |  | 2022-03-01 | 2022-03-28
This is an empty row
This row marks the end of the Project Schedule. DO NOT enter anything in this row. Insert new rows ABOVE this one to continue building out your Project Schedule. | Insert new rows ABOVE this one

## Members
Team Members
| Alex Hoi Chu | Dimitri Vlachos | Freda Xiaoyun Yu | Jeremy Matthews | Sharif Khan
| · Strengths: Despite having no prior knowledge on computer science, I have been scoring >80% on my previous modules, many times >90% so I’m confident that whatever challenge comes my way in terms of the project, I could handle it. I’ve also been allotting time per week specifically to university study so would work in a consistent, predictable rate. | · My strengths: Programming, logic and maths. I have always done really well with these. I am also fairly competent at writing and communication. | · Strengths: math, stats (have some knowledge), music (piano), paper writing, background research, communication, questionnaire, time management, etc. I have done two projects both are user-oriented in high school, using basic statistics methods. | · Strengths are programming, maths and graphics. I am strong at laying out technical systems and planning technical roadmaps. I have also been working with the Agile methodology for about a decade at work (although at times it is modified to meet the project needs). I have a previous degree in art/animation, but those skills may be a bit rusty.
| · Weaknesses: I’ve had no programming knowledge prior to starting the university degree so the number of languages I know is limited to only what was taught in the modules. My work days are not predicated by me so there may be times when I’m unexpectedly absent when I’m needed. | · Weaknesses: Theory and time management. I can be quite bad with my time, even though I am aware of it, I tend to show up late to meetings and events through my own poor planning. I also struggle to memorise or internalise purely theoretical work, preferring more practical tasks where I get to build something. | · Weaknesses: web dev, html...And I’m not an experienced programmer. | · Weaknesses are around HTML and CSS type of work. Most of my experience is in video games, so I just do not have as much experience in this area
| · Languages: javascript, html, css(I got >95% in the final project in Web Dev so I’m confident in those three), c++, python | · Languages: Java, Javascript, C#, Python, HTML and SQL. Prior to this degree I completed all the programming modules of a previous degree and am very confident in my Java abilities, I got 100% for my modules in it. I also did SQL and HTML. I also taught myself C# while learning to code and make games in Unity. | · Languages: python, p5.js, c++ | · Languages I've worked with are C/C++, C#, Java, JavaScript and some Python. I'm comfortable working/learning which ever language the group would like to work with. I would recommend JavaScript, as this course seems to use it a fair bit and it is a very useful language once we are done the degree.
| · Prior experience: None and none | · Prior experience: Mostly completed a BSc Computing and Information Systems degree before I switched over to this degree course. | · Prior experience: None | · Prior experience - I started out as an artist/animator in the games industry but quickly transitioned into technical art and then engineering 16 years ago. I worked for Electronic Arts for 10 of those years as a software engineer. I focused mostly on gamplay and AI. Had to opportunity to be involved with The Simpsons:Tapped Out, NBA Live, NBA Jam Mobile, Peggle and a Star Wars game that has not been released yet. I also worked at small company called Kabam as a rendering engineer and worked on Marvel: Contest of Champions, Marvel: Realm of Champions and Disney's Mirrorverse. Now I am at a smaller company with a group of friends, making games for the fun of making games
| · Expected grade: I would expect above 80% but going for 100% would be the dream | · Expected grade: I would love to get a high grade in this module. So I am expecting 80%+. | · Expected grade: I heard the grades for this module are generally low, so I don’t expect much, but I definitely will aim for a high score. | · I usually try to get the best grade I can achieve within reason. I am part time in this course with a full time job and 2 children, but I have been able to manage 85+% in most of my other courses.
| · Expected hours: I generally spend >20 hours a week on university work but since most work from the other modules is just the learning itself and no practical work, I could put in 10 hours, more if there is not much from other modules. | · Expected hours: I work on this course full time, so I can put in 8+ hours a day, if not more if necessary, preferably during the week, but I am flexible. | · Expected hours: I have some family issue. But other than that, I am full-time on this degree. So I don’t know but I will try my best, perhaps 8 hrs/week. At the beginning of each month (like from 6th to 11th or so, I always have some illness, girls’ issue you know...). | · With being part time student with a full time job and family, I may not be able to put in as many hours as others, but will aim for between 4 to 6 per week. This may fluctuate a little when I am chrunching at work, but will try to give this as much attention as I can.
| · How I use computers outside of university work: play games on my computer, read books on my phone and watch youtube, my work does not require computers | · How I use computers outside of Uni: I spend a lot of time on the computer or on electronic devices in general. I communicate online, I play games, I do write some code and scripts, though nothing too extensive, watch youtube, browse the internet and such. My work does require a computer, though just for basic excel tasks and emails. But I would consider myself a very competent computer user. | · Inspirations on the topic we will do: Nothing appears on my mind but I will summarize—I use phones very often...(1) I am an advanced user for a clothes fashion game, you know the clothes there are all in famous brands and they make it looks real. (2) Also I use QQ and a karaoke app, but I don’t think we could do a social software soon. (3) We can make a website to display music theories and instruments museum, to let beginners fall in love with music and learn some basic knowledges—I’m good at music. (4) Also we can do a cool math website, where we do our inspirations and explanations for brilliant math ideas, whether in blogs or in videos or in photos. We also can tell stories about mathematicians. I think it would be a very good material for our applications of further study. | · My use of computers outside of university focuses mostly around programming for work and fun. I also play around with IoT type things with RPi and Arduino for fun. If I have time, I play some games and use social media.
| · Willingness to communicate: I am willing to use any software to communicate with, including zoom, but don’t currently have a headset to talk with. I do have the webcam I used for Graphics Programming which has been used as a microphone, so if we do end up doing voice based meeting, for the first few meetings, I would sound a bit odd | · How will I be willing to communicate: I agree that just sticking to slack might be difficult. I suggest we try arrange, perhaps a weekly meeting either on Zoom, or Skype or Discord. Try to work all our timezones out. I am willing to use any app for it, not just the ones I mentioned. | · Willingness to communicate: I’m not good at oral English, but will try. I am active. Writing will be best to state my ideas clearly I think. But if you have meetings, I will attend. I also would like to gather our group communication evidences. | · I'm willing to communicate any way that the group would like. Slack is probably the best place to keep all of our written communication as we know everyone has access to it. Google meetings are usually pretty good for voice and video. It may be difficult to find a time for weekly meetings for everyone as we seem to be pretty spread out time zone wise. We may want to either take notes at the meetings for people who are unable to attend, or, record the meetings and put the video up on a shared Google drive for people to watch later (I did this at Kabam with pretty good results).
| · Time zone: UTC +12:00, Auckland, New Zealand | · Timezone: UTC + 2 (Johannesburg, South Africa) | · Time zone: China UTC+8 | Prince Edward Island, Canada. My time zone is Atlantic Standard Time (GMT -4)
| · Preferred software to make for the project: A visual programming language, which like an IDE is used to create code but instead of just lines of code, the interaction between different components are shown visually. The interface is also a ‘drag and drop’ one so the interaction could be seen and controlled more easily. An example of one such program that exists is Pyplan: https://pyplan.org/. The wikipedia page for this type of software: https://en.wikipedia.org/wiki/Visual_programming_language | · What kind of software project would I like to make: I'm not sure exactly what I would like to do. We definitely need to discuss it more. However, I do have some preferences. I would also like to use an IDE and an object oriented language. It would be good to use something that we are all at least passingly familiar with. Can we do literally anything? If so then perhaps we should make something useful, or interesting, maybe making use of some APIs like google's. Or maybe we should make a game! There's a lot of ways it can go | · Preferred software to make for the project: I don’t think a new programming language is good for us. It’s acceptable to use P5.js to make a small game (I’ve learned Graphics Programming last term); or just make a website (though I’m not fluent on using html). I’ve learned JUCE in C++ language in Object-Oriented Programming module, but I’m not confident on doing that. | · I think it would be pretty interesting to make some educational software that used video game techniques in its teaching method. I am open to any sort of software though.

## (About)
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. TimeSheet About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.